## TIM-001_Design_and_Theme_Lock
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-001-01 | Brand Standards and Style Themes Lock | Critical | 2026-04-01 | 2026-04-05 | 4 |  | In Progress | None | Owner | Primary styling baseline
TIM-001-02 | Room-by-Room Design Specs Map | High | 2026-04-04 | 2026-04-10 | 6 |  | In Progress | TIM-001-01 | Owner | Inventory lists for procurement
TIM-001-03 | Brand Voice and Copywriting Strategy | Medium | 2026-04-06 | 2026-04-10 | 4 |  | Planned | TIM-001-01 | Owner | Guest persona focus

## TIM-002_Procurement_Ordering_Wi
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-002-01 | Primary Furnishing Order Launch | Critical | 2026-04-08 | 2026-04-12 | 4 |  | Planned | TIM-001-02 | Owner | Prioritize long-lead items
TIM-002-02 | Amenity and Tech Procurement | High | 2026-04-11 | 2026-04-20 | 9 |  | Planned | TIM-002-01 | Owner | Focus on social island items
TIM-002-03 | Linen and Consumable Bulk Order | Medium | 2026-04-15 | 2026-04-18 | 3 |  | Planned | TIM-002-01 | Owner | Linen system setup
TIM-002-04 | Logistics and Delivery Coordination | High | 2026-04-12 | 2026-04-20 | 8 |  | Planned | TIM-002-01 | Owner | Align with install dates

## TIM-003_Install_and_Staging_Exe
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-003-01 | Furniture Assembly and Staging | High | 2026-04-15 | 2026-04-25 | 10 |  | Planned | TIM-002-02 | Owner | Turnover-style staging QA
TIM-003-02 | Smart Home and Tech Deployment | High | 2026-04-20 | 2026-04-27 | 7 |  | Planned | TIM-003-01 | Owner | Smart lock and mesh validation
TIM-003-03 | Final Site Cleaning and Prep | High | 2026-04-25 | 2026-04-27 | 2 |  | Planned | TIM-003-01 | Owner | White-glove sanitization
TIM-003-04 | Amenity Stocking and QA Pass | Medium | 2026-04-26 | 2026-04-27 | 1 |  | Planned | TIM-003-03 | Owner | Inventory verification

## TIM-004_Photo_and_Listing_Asset
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-004-01 | Professional Media Capture (Twilight/3D) | Critical | 2026-04-22 | 2026-04-26 | 4 |  | Planned | TIM-003-02 | Owner | Follow hero shot list
TIM-004-02 | Listing Description and Content Drafting | Medium | 2026-04-24 | 2026-04-30 | 6 |  | Planned | TIM-004-01 | Owner | Optimize for SEO Keywords
TIM-004-03 | Photo Selection and Post-Production | High | 2026-04-27 | 2026-04-30 | 3 |  | Planned | TIM-004-01 | Owner | Top 5 "Hero" shots focus
TIM-004-04 | Channel Setup (Airbnb/VRBO) | High | 2026-04-28 | 2026-05-02 | 4 |  | Planned | TIM-004-02 | Owner | Draft listing creation

## TIM-005_Pricing_and_Promotions_
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-005-01 | Pricing Engine Rules and Seasonality | High | 2026-04-25 | 2026-04-28 | 3 |  | Planned | TIM-004-01 | Owner | Anchor in 78744 benchmarks
TIM-005-02 | Promotion Stack and Discount Launch | Medium | 2026-04-28 | 2026-05-02 | 4 |  | Planned | TIM-005-01 | Owner | Enable 15% new listing promo
TIM-005-03 | Occupancy Target Calibration | Medium | 2026-04-30 | 2026-05-03 | 3 |  | Planned | TIM-005-01 | Owner | Set baseline for first 90 days
TIM-005-04 | Channel Sync and Availability Lock | High | 2026-05-02 | 2026-05-04 | 2 |  | Planned | TIM-005-02 | Owner | Verify calendar sync

## TIM-006_Compliance_Verification
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-006-01 | STR Permit and Compliance Finalization | Critical | 2026-04-10 | 2026-05-01 | 21 |  | In Progress | TIM-001-02 | Owner | City of Austin lead times
TIM-006-02 | Insurance and Tax Setup Verification | High | 2026-04-20 | 2026-05-05 | 15 |  | Planned | TIM-006-01 | Owner | Verify STR coverage
TIM-006-03 | Smart Lock Compliance Check | High | 2026-04-25 | 2026-04-30 | 5 |  | Planned | TIM-003-02 | Owner | Safety code validation
TIM-006-04 | House Rules and Policy Review | Medium | 2026-04-30 | 2026-05-04 | 4 |  | Planned | TIM-006-01 | Owner | Align with legal strategy

## TIM-007_Go-Live_Readiness_Revie
task_id | task_name | priority | start_date | end_date | duration_days | actual_completion | status | dependency | owner | notes
TIM-007-01 | Final Readiness Walkthrough and Audit | Critical | 2026-05-03 | 2026-05-05 | 2 |  | Planned | TIM-004¦TIM-005¦TIM-006 | Owner | Gate check for go-live
TIM-007-02 | Listing Go-Live and Booking Launch | Critical | 2026-05-06 | 2026-05-07 | 1 |  | Planned | TIM-007-01 | Owner | Formal market launch
TIM-007-03 | Guest Communication System Test | High | 2026-05-05 | 2026-05-06 | 1 |  | Planned | TIM-007-01 | Owner | Message template validation
TIM-007-04 | Calendar and Payout Audit | High | 2026-05-06 | 2026-05-07 | 1 |  | Planned | TIM-007-02 | Owner | Financial reconciliation